## Sheet1
scenarioId | scenarioName | scenarioProjectId | projectId | projectKey | projectName | projectType | projectStart | projectFinish | projectManagerId | projectManagerName | projectCostType | projectStatus | projectNotes | projectRankCategory | projectRank | projectLastChanged | projectTotalAllocationsHours | projectPlannedAllocationsHoursTotal | projectTotalBenefit | projectPlannedBenefitTotal | projectTotalNetValue | projectPlannedNetValueTotal | projectTotalCostCapex | projectPlannedCapexTotal | projectTotalCostOpex | projectPlannedOpexTotal | projectTotalCost | projectPlannedCostsTotal | projectTotalCostAllocations | projectPlannedAllocationCostsTotal | projectTotalCostFinancials | projectPlannedFinancialEventsCostsTotal | projectActualFinancialEventsCostsTotal | projectActualFinancialEventsCostsCapex | projectActualFinancialEventsCostsOpex | projectActualFinancialEventsBenefitTotal | projectTotalActualTimeWorkedHours | projectApprovedTotalEffortHours | projectRemainingAllocationsFromTodayHours | projectFutureAllocationsHours | projectAllocationEstimateAtCompletionHours | projectApprovedCapexBudget | projectApprovedOpexBudget | projectApprovedBudget | businessGoalName | businessGoalColor | programName | projectAllocationPercentageOfCompletion | cust_launch_quarter | cust_gantt_include | cust_hero | cust_stage_gate | cust_department | cust_launch_type | cust_description | obs_Role | obs_Department | obs_Location | obs_Product Line
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | e0a29c10-3a61-48bb-8738-2cc4498f9c15 | 3040819f-eff8-4836-a661-c84a43edd1ff | MPP-40 | DS PIU | New Product Development | 2024-11-15 | 2025-09-30 |  |  | OPEX |  |  | Regular | 1 | 2025-07-14T17:51:51Z | 206.4 | 206.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.2 | 163.2 | 206.4 | 0 | 0 | 0 |  |  |  | 0.2093 | 2025 Q3 | Yes | SYSTEMS - DS | Stage 5: FEC |  | Medium |  |  |  |  | 1. Drawer System
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 5a0746f2-d00b-4aca-903c-5f4023cf24b9 | 02c6a1eb-be43-49f8-9edf-c6691ece15b2 | MPP-21 | Piecekeeper PuzzleFoam | New Product Development | 2024-11-21 | 2025-09-23 |  |  | OPEX |  |  | Regular | 2 | 2025-07-14T17:51:51Z | 34.4 | 34.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2 | 27.2 | 34.4 | 0 | 0 | 0 |  |  |  | 0.2093 | 2025 Q3 | Yes | EXPAND D-CO | Stage 6: TKO |  | Medium |  |  |  |  | 6. D-cosystem > a. Misc Accys
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 5e7d597d-3f37-4c8d-9e86-6bb784818d2a | cc30b33c-e6d6-4a26-b47d-6199400ceaa1 | MPP-20 | D-co Mounting | New Product Development | 2024-05-27 | 2025-09-23 |  |  | OPEX |  |  | Regular | 3 | 2025-07-14T17:51:51Z | 102.4 | 102.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.6 | 37.6 | 102.4 | 0 | 0 | 0 |  |  |  | 0.63281 | 2025 Q3 | Yes | EXPAND D-CO | Stage 6: TKO |  | Small |  |  |  |  | 6. D-cosystem > a. Misc Accys
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | e99ef894-5436-4ef3-b42f-a9926e890cd0 | ec523b77-a4df-43e5-9075-757f63837c06 | MPP-39 | No Drill & 8ft Brackets | New Product Development | 2025-02-27 | 2026-06-30 |  |  | OPEX |  |  | Regular | 4 | 2025-07-14T17:51:51Z | 213.2 | 213.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 138 | 213.2 | 0 | 0 | 0 |  |  |  | 0.35272 | 2025 Q4 | Yes | SYSTEMS - CG | Stage 8: PVT |  | Small |  |  |  |  | 2. CargoGlide
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 8efc0e8e-ddf3-46db-ad48-33e7bd99327b | 832a7434-68ff-454e-b8e7-13fe9d91db3a | MPP-48 | Lunchbox Handle 3.0 | Continuous Improvement | 2024-08-01 | 2025-11-30 |  |  | OPEX |  |  | Regular | 5 | 2025-07-14T17:51:51Z | 288 | 288 | 0 | 0 | -150000 | -150000 | 150000 | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 266.4 | 266.4 | 288 | 0 | 0 | 0 |  |  |  | 0.075 | 2025 Q4 | Yes | EXPAND D-CO | Stage 12: P-L |  | Small |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | fce72968-5d29-46c5-a293-5ec819445155 | 3997cba7-2218-41f7-9327-bdeec9481198 | MPP-43 | Toolbox 2.0 | New Product Development | 2023-06-24 | 2026-03-31 |  |  | OPEX |  |  | Regular | 6 | 2025-07-14T17:51:51Z | 4712.8 | 4712.8 | 0 | 0 | -1800000 | -1800000 | 1800000 | 1800000 | 0 | 0 | 1800000 | 1800000 | 0 | 0 | 1800000 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 4208.8 | 4208.8 | 4712.8 | 0 | 0 | 0 |  |  |  | 0.10694 | 2026 Q1 | Yes | TB = HERO | Stage 6: TKO |  | Flagship |  |  |  |  | 3. ToolBox
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | d572a611-74ea-4763-b7bb-4fcd6a98a187 | d45c72cd-0a3b-4b48-a434-e2a3ffd8ba0c | MPP-33 | Payloader 64L and 164L | New Product Development | 2024-09-19 | 2026-03-31 |  |  | OPEX |  |  | Regular | 7 | 2025-07-14T17:51:51Z | 1520.8 | 1520.8 | 0 | 0 | -1200000 | -1200000 | 1200000 | 1200000 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 1470.4 | 1470.4 | 1520.8 | 0 | 0 | 0 |  |  |  | 0.03314 | 2026 Q1 | Yes | EXPAND D-CO | Stage 5: FEC |  | Flagship |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 9ffe7f33-f7e6-4abc-90bb-7bc3506a1817 | 722f94f1-72df-4f83-8af5-fe9d6a7de2a3 | MPP-22 | Small Parts Pack Rat Killer | New Product Development | 2025-04-03 | 2026-06-30 |  |  | OPEX |  |  | Regular | 8 | 2025-07-14T17:51:51Z | 388.8 | 388.8 | 0 | 0 | -100000 | -100000 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 252 | 388.8 | 0 | 0 | 0 |  |  |  | 0.35185 | 2026 Q1 | Yes | EXPAND D-CO | Stage 2: BRD |  | Medium |  |  |  |  | 6. D-cosystem > a. Misc Accys
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | d6dba42a-c7d6-4923-ab84-123d65f825d1 | 0bbbcd29-601f-430b-8eaa-82229246dc5b | MPP-57 | Milwaukee | Business Development | 2024-09-01 | 2026-06-30 |  |  | OPEX |  |  | Regular | 9 | 2025-07-14T17:51:51Z | 1064 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013.6 | 1013.6 | 1064 | 0 | 0 | 0 |  |  |  | 0.047368 | 2026 Q1 | Yes | SYSTEMS - DS |  |  | Medium |  |  |  |  | 9. Partner / Misc
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | e5dc9081-8981-464d-8705-ebfe304f5460 | 893d10d3-dd33-4223-8a03-05de98fd333f | MPP-52 | TB 2.0 Hooks | New Product Development | 2024-06-01 | 2026-03-31 |  |  | OPEX |  |  | Regular | 10 | 2025-07-14T17:51:51Z | 83.2 | 83.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 76 | 83.2 | 0 | 0 | 0 |  |  |  | 0.086538 | 2026 Q1 | Yes | TB = HERO | Stage 6: TKO |  | Small |  |  |  |  | 3. ToolBox
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 27fc04fb-338d-47b5-b931-dc9d49568708 | 80537a8f-259d-4cad-aff3-274663ee3640 | MPP-51 | Consumer SUV DS | New Product Development | 2025-02-01 | 2026-06-30 |  |  | OPEX |  |  | Regular | 11 | 2025-07-14T17:51:51Z | 4323.2 | 4323.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4251.2 | 4251.2 | 4323.2 | 0 | 0 | 0 |  |  |  | 0.016654 | 2026 Q2 | Yes | SYSTEMS - DS | Stage 3: xRD |  | Large |  |  |  |  | 1. Drawer System
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 568d860c-6d36-4074-9f8a-26b5df9d3949 | 275bcd5b-cf42-469f-96d4-23981471f206 | MPP-44 | CG XL 2.0 | New Product Development | 2025-01-01 | 2026-06-30 |  |  | OPEX |  |  | Regular | 12 | 2025-07-14T17:51:51Z | 3406.4 | 3406.4 | 0 | 0 | -150000 | -150000 | 150000 | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 3284 | 3284 | 3406.4 | 0 | 0 | 0 |  |  |  | 0.035932 | 2026 Q2 | Yes | SYSTEMS - CG | Stage 3: xRD |  | Medium |  |  |  |  | 2. CargoGlide
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 958d89bb-a6cb-460a-9ad6-e6c7f60ccb51 | 4f82f8a6-a901-46d1-9a09-e03bb4c40cb2 | MPP-56 | Bike Rack Partnership | Business Development | 2024-07-01 | 2026-06-30 |  |  | OPEX |  |  | Regular | 13 | 2025-07-14T17:51:51Z | 932 | 932 | 0 | 0 | -200000 | -200000 | 200000 | 200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 896 | 896 | 932 | 0 | 0 | 0 |  |  |  | 0.038627 | 2026 Q2 | Yes | SYSTEMS - DS |  |  | Medium |  |  |  |  | 9. Partner / Misc
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | c4998711-9daf-4c1d-8cd3-0d1374a45e8a | 03c89ea2-ee15-4bc3-952a-df4aadb0dc9b | MPP-34 | Honcho 16L & 100L | New Product Development | 2024-10-02 | 2026-08-31 |  |  | OPEX |  |  | Regular | 14 | 2025-07-14T17:51:51Z | 4874.4 | 4874.4 | 0 | 0 | -1800000 | -1800000 | 1800000 | 1800000 | 0 | 0 | 1800000 | 1800000 | 0 | 0 | 1800000 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 3533.2 | 3533.2 | 4874.4 | 0 | 0 | 0 |  |  |  | 0.27515 | 2026 Q3 | Yes | EXPAND D-CO | Stage 3: xRD |  | Flagship |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 935be652-8ad4-4ddd-930f-6bad758b44ee | eac4419a-2a9e-4b3d-aaae-6b21c8ced36f | MPP-41 | 1/2 Drawer System | New Product Development | 2025-04-03 | 2026-09-30 |  |  | OPEX |  |  | Regular | 15 | 2025-07-14T17:51:51Z | 2862.4 | 2862.4 | 0 | 0 | -150000 | -150000 | 150000 | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 2862.4 | 2862.4 | 2862.4 | 0 | 0 | 0 |  |  |  | 0 | 2026 Q3 | Yes | SYSTEMS - DS | Stage 2: BRD |  | Large |  |  |  |  | 1. Drawer System
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 8773717e-d35c-4ac6-b63f-5ed3cc6ac8b9 | 551ef86b-c035-4709-89b5-d6b35649ead1 | MPP-63 | CG Divider System | New Product Development | 2025-07-01 | 2026-10-31 |  |  | OPEX |  |  | Regular | 16 | 2025-07-14T17:51:51Z | 1580.8 | 1580.8 | 0 | 0 | -50000 | -50000 | 50000 | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 1573.6 | 1573.6 | 1580.8 | 0 | 0 | 0 |  |  |  | 0.004555 | 2026 Q4 | Yes | SYSTEMS - CG |  |  | Small |  |  |  |  | 2. CargoGlide
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 31d9319a-a0a9-468f-80b7-35287f4da7f1 | a989a21f-3bd5-408b-b254-2ff62dd04079 | MPP-59 | Honcho 160L | New Product Development | 2025-01-01 | 2027-03-31 |  |  | OPEX |  |  | Regular | 17 | 2025-07-14T17:51:51Z | 1619.2 | 1619.2 | 0 | 0 | -800000 | -800000 | 800000 | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0 | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 1579.6 | 1579.6 | 1619.2 | 0 | 0 | 0 |  |  |  | 0.024457 | 2027 Q1 | Yes | EXPAND D-CO |  |  | Flagship |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | a4cb7440-0acd-4b67-acc5-a83e26b7432a | 4231b927-0f75-455f-803c-8088f227546f | MPP-66 | D-co Softgoods Round 1 | New Product Development | 2025-04-01 | 2027-06-30 |  |  | OPEX |  |  | Regular | 18 | 2025-07-14T17:51:51Z | 2870.4 | 2870.4 | 0 | 0 | -100000 | -100000 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 2820 | 2820 | 2870.4 | 0 | 0 | 0 |  |  |  | 0.017559 | 2027 Q1 | Yes | EXPAND D-CO |  |  | Medium |  |  |  |  | 6. D-cosystem > c. Softgoods
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 6ab86074-2c9b-48de-acfb-4d391b187d3f | e29549d0-f87c-4326-9455-f638b1c4b565 | MPP-65 | D-co Power Box | New Product Development | 2025-01-01 | 2027-03-31 |  |  | OPEX |  |  | Regular | 19 | 2025-07-14T17:51:51Z | 2139.2 | 2139.2 | 0 | 0 | -100000 | -100000 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 2096 | 2096 | 2139.2 | 0 | 0 | 0 |  |  |  | 0.020194 | 2027 Q1 | Yes | EXPAND D-CO |  |  | Medium |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | c08793de-c68f-44ea-a46c-bb4714b1098d | ae2a54dd-b79f-450e-8dd9-ec9a7bb052a5 | MPP-55 | DS D-co Mounting | New Product Development | 2024-11-01 | 2027-03-31 |  |  | OPEX |  |  | Regular | 20 | 2025-07-14T17:51:51Z | 2027.2 | 2027.2 | 0 | 0 | -150000 | -150000 | 150000 | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 1991.2 | 1991.2 | 2027.2 | 0 | 0 | 0 |  |  |  | 0.017758 | 2027 Q1 | Yes | EXPAND D-CO |  |  | Medium |  |  |  |  | 6. D-cosystem > a. Misc Accys
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 2999e3f2-01c8-4db3-bfff-e112f9343ac4 | 1b59f749-74bc-4a61-a126-511be3a94c51 | MPP-62 | Honcho Lid Org | New Product Development | 2024-08-01 | 2027-03-31 |  |  | OPEX |  |  | Regular | 21 | 2025-07-14T17:51:51Z | 187.2 | 187.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.2 | 187.2 | 187.2 | 0 | 0 | 0 |  |  |  | 0 | 2027 Q1 | Yes | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > a. Misc Accys
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | e3c21283-ccc4-498a-b319-03f7eddc1314 | cf1da2ea-a402-4068-8947-e9b39ba2905c | MPP-64 | TB / DS Lighting | New Product Development | 2025-10-01 | 2027-03-31 |  |  | OPEX |  |  | Regular | 22 | 2025-07-10T16:24:34Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2027 Q1 | Yes | TB = HERO |  |  | Small |  |  |  |  | 3. ToolBox
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | ec786fe7-c03e-477f-b7d5-335376c3e6ca | f56a46b1-b102-41b2-9899-9c66d02f120a | MPP-58 | Garage Rack | New Product Development | 2025-04-01 | 2027-11-30 |  |  | OPEX |  |  | Regular | 23 | 2025-07-14T17:51:51Z | 8035.2 | 8035.2 | 0 | 0 | -1250000 | -1250000 | 1250000 | 1250000 | 0 | 0 | 1250000 | 1250000 | 0 | 0 | 1250000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 8006.4 | 8006.4 | 8035.2 | 0 | 0 | 0 |  |  |  | 0.003584 | 2027 Q3 | Yes | EXPAND D-CO | Stage 1: PRFAQ |  | Flagship |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 2effde98-1a97-4041-bd00-79fde43a0d81 | 0b1f8c7f-d37d-4624-9ccb-1a31830a11cf | MPP-60 | Payloaders '27 (TBD) | New Product Development | 2026-01-01 | 2027-08-31 |  |  | OPEX |  |  | Regular | 24 | 2025-07-14T17:51:51Z | 1591.2 | 1591.2 | 0 | 0 | -750000 | -750000 | 750000 | 750000 | 0 | 0 | 750000 | 750000 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 1591.2 | 1591.2 | 1591.2 | 0 | 0 | 0 |  |  |  | 0 | 2027 Q3 | Yes | EXPAND D-CO |  |  | Large |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 8e888b33-0239-4e73-91d7-9d002ed21f54 | c58e23c2-95b9-42c8-9383-f617d34cdfc9 | MPP-45 | Cap System | New Product Development | 2024-07-01 | 2028-03-31 |  |  | OPEX |  |  | Regular | 25 | 2025-07-14T17:51:51Z | 22016 | 22016 | 0 | 0 | -3400000 | -3400000 | 3400000 | 3400000 | 0 | 0 | 3400000 | 3400000 | 0 | 0 | 3400000 | 3400000 | 0 | 0 | 0 | 0 | 0 | 0 | 21951.2 | 21951.2 | 22016 | 0 | 0 | 0 |  |  |  | 0.002943 | 2027 Q4 | Yes | VEHICLE EXPANSION | Stage 2: BRD |  | Flagship |  |  |  |  | 4. Cap System
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 25ae20a8-be19-4145-9629-73a6e5f984e1 | b0f83a34-1560-4a38-b7c9-1d4409ee42eb | MPP-47 | Sidebox | New Product Development | 2025-01-01 | 2027-11-30 |  |  | OPEX |  |  | Regular | 26 | 2025-07-14T17:51:51Z | 5262.4 | 5262.4 | 0 | 0 | -400000 | -400000 | 400000 | 400000 | 0 | 0 | 400000 | 400000 | 0 | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 5262.4 | 5262.4 | 5262.4 | 0 | 0 | 0 |  |  |  | 0 | 2027 Q4 | Yes | VEHICLE EXPANSION | Stage 1: PRFAQ |  | Medium |  |  |  |  | 4. Cap System
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 38d2c378-3a23-49d7-aab4-64f6c6e9f156 | 25c056b1-150c-4701-bb98-9a689e6f4d53 | MPP-69 | Hard Tonneau Cover | New Product Development | 2025-11-01 | 2028-07-02 |  |  | OPEX |  |  | Regular | 27 | 2025-07-14T17:51:51Z | 9929.6 | 9929.6 | 0 | 0 | -2000000 | -2000000 | 2000000 | 2000000 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 9929.6 | 9929.6 | 9929.6 | 0 | 0 | 0 |  |  |  | 0 | 2028 Q1 | Yes | VEHICLE EXPANSION |  |  | Flagship |  |  |  |  | 5. Other Vehicle
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 0c478d2a-ca91-4dc3-bbf0-39bbc575d555 | b5df1e75-743a-4e6b-a03b-783ca9122e0c | MPP-68 | Dog Kennel | New Product Development | 2026-04-01 | 2028-06-30 |  |  | OPEX |  |  | Regular | 28 | 2025-07-14T17:51:51Z | 1631.2 | 1631.2 | 0 | 0 | -1750000 | -1750000 | 1750000 | 1750000 | 0 | 0 | 1750000 | 1750000 | 0 | 0 | 1750000 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 1631.2 | 1631.2 | 1631.2 | 0 | 0 | 0 |  |  |  | 0 | 2028 Q2 | Yes | EXPAND D-CO |  |  | Flagship |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | a0389fc8-c26e-4135-8812-1ad1b343df77 | 91674d8e-7975-4c1f-8238-bc256b6813c8 | MPP-67 | D-co Softgoods Round 2 | New Product Development | 2026-10-01 | 2028-12-30 |  |  | OPEX |  |  | Regular | 29 | 2025-07-10T16:25:22Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2028 Q2 | Yes | EXPAND D-CO |  |  | Large |  |  |  |  | 6. D-cosystem > c. Softgoods
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | c8a38370-5c48-471c-9347-52320382e761 | d1993c94-0262-4534-99e3-d6d77170e472 | MPP-71 | DECKED Trailer | New Product Development | 2026-06-03 | 2028-11-30 |  |  | OPEX |  |  | Regular | 30 | 2025-07-14T17:51:51Z | 827.2 | 827.2 | 0 | 0 | -750000 | -750000 | 750000 | 750000 | 0 | 0 | 750000 | 750000 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 827.2 | 827.2 | 827.2 | 0 | 0 | 0 |  |  |  | 0 | 2028 Q3 | Yes | VEHICLE EXPANSION |  |  | Flagship |  |  |  |  | 5. Other Vehicle
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | d2b4b8a5-d703-4a2c-836f-f96ff0fd3c77 | 21c51380-0f13-439c-a9c4-3f8a3cb756f2 | MPP-53 | D-co Colorways | New Product Development | 2024-05-01 | 2025-03-31 |  |  | OPEX |  |  | Regular | 31 | 2025-06-17T17:15:46Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | EXPAND D-CO | [7 empty] | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 830d2014-1e44-4690-845f-8414cee1426c | cc8914cd-e656-4a9c-9c5f-907cb3ba2dc4 | MPP-72 | Honcho [40L] | New Product Development | 2026-10-01 | 2028-08-31 |  |  | OPEX |  |  | Regular | 32 | 2025-07-14T17:51:51Z | 211.2 | 211.2 | 0 | 0 | -500000 | -500000 | 500000 | 500000 | 0 | 0 | 500000 | 500000 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 211.2 | 211.2 | 211.2 | 0 | 0 | 0 |  |  |  | 0 | 2028 Q3 | Yes | EXPAND D-CO |  |  | Medium |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 46f8d125-3384-40ba-b7df-fb6acf6c39ca | adfeabf4-9173-489f-b152-be7fbb445093 | MPP-95 | Honcho Rebuild | New Product Development | 2026-10-01 | 2028-08-31 |  |  | OPEX |  |  | Regular | 33 | 2025-07-14T17:51:51Z | 52.8 | 52.8 | 0 | 0 | -750000 | -750000 | 750000 | 750000 | 0 | 0 | 750000 | 750000 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 52.8 | 52.8 | 52.8 | 0 | 0 | 0 |  |  |  | 0 | 2028 Q3 | Yes | EXPAND D-CO |  |  | Medium |  |  |  |  | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 64dd465f-4712-4d60-ac3f-8a2edfa24a20 | d903b56a-1877-428d-a551-60406f96f198 | MPP-74 | D-co Colors | New Product Development | 2025-01-01 | 2028-12-31 |  |  | OPEX |  |  | Regular | 34 | 2025-07-14T17:51:51Z | 621.2 | 621.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610.4 | 610.4 | 621.2 | 0 | 0 | 0 |  |  |  | 0.017386 | On-going | Yes | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | b1b0351a-38a7-4f4a-b689-37cc659de5b1 | 4d540ff7-b17a-42ed-bc05-4c61aa2f0491 | MPP-54 | D-co Kits | New Product Development | 2024-09-01 | 2028-12-31 |  |  | OPEX |  |  | Regular | 35 | 2025-07-14T17:51:51Z | 517.2 | 517.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506.4 | 506.4 | 517.2 | 0 | 0 | 0 |  |  |  | 0.020882 | On-going | Yes | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 115fe5f2-18c3-4fb9-99ff-f54b471b4241 | 6cc065c2-a859-4ebc-88a5-cff93788ef1c | MPP-49 | DS - Integrations | Continuous Improvement | 2023-01-01 | 2030-12-31 |  |  | OPEX |  |  | Regular | 36 | 2025-07-14T17:51:51Z | 1336 | 1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1318 | 1318 | 1336 | 0 | 0 | 0 |  |  |  | 0.013473 | On-going | Yes | CI | Stage 12: P-L |  | Small |  |  |  |  | 1. Drawer System
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 274ce275-b751-422e-8509-d8424874e81a | 74673c06-69fb-4954-b18b-2daabf367aa7 | MPP-61 | TB 2.0 Color | New Product Development | 2025-01-01 | 2029-12-31 |  |  | OPEX |  |  | Regular | 37 | 2025-07-14T17:51:51Z | 118.4 | 118.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.2 | 111.2 | 118.4 | 0 | 0 | 0 |  |  |  | 0.060811 | On-going | Yes | TB = HERO |  |  | Small |  |  |  |  | 3. ToolBox
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | e68b1f88-9ee1-49dd-b955-a34fad610261 | 11291b30-1471-4a04-bbc2-fd82f387bcdf | MPP-46 | DS - CI | Continuous Improvement | 2023-10-02 | 2030-12-31 |  |  | OPEX |  |  | Regular | 38 | 2025-07-14T17:51:51Z | 2672 | 2672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 2600 | 2672 | 0 | 0 | 0 |  |  |  | 0.026946 | On-going | Yes | CI | Stage 12: P-L | [6 empty] | 1. Drawer System
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 21c36697-50fd-4490-9999-d771340e7ee7 | 839feaaa-566a-4327-8d6d-6cb124418189 | MPP-94 | D-co - CI | Continuous Improvement | 2025-01-01 | 2030-12-31 |  |  | OPEX |  |  | Regular | 39 | 2025-07-14T17:51:51Z | 1885.6 | 1885.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1878.4 | 1878.4 | 1885.6 | 0 | 0 | 0 |  |  |  | 0.003818 | On-going | Yes | CI | [7 empty] | 6. D-cosystem
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | b6ad1837-892e-4cc2-b152-aa44d58deca7 | 00f92c5a-d405-4b36-87cb-b792e9050cc0 | MPP-76 | TB - CI | Continuous Improvement | 2026-01-01 | 2030-12-31 |  |  | OPEX |  |  | Regular | 40 | 2025-07-14T17:51:51Z | 191.2 | 191.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191.2 | 191.2 | 191.2 | 0 | 0 | 0 |  |  |  | 0 | On-going | Yes | CI | [7 empty] | 3. ToolBox
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 96e5704a-36a2-4791-93ec-fe889c7c9fd0 | 435a313e-e43e-436e-be7e-be6faa365db6 | MPP-75 | CG - CI | Continuous Improvement | 2024-01-01 | 2030-12-31 |  |  | OPEX |  |  | Regular | 41 | 2025-07-14T17:51:51Z | 3228 | 3228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3055.2 | 3055.2 | 3228 | 0 | 0 | 0 |  |  |  | 0.053532 | On-going | Yes | CI | [7 empty] | 2. CargoGlide
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 97a0b8d1-9f5a-4c5f-b2c1-29a81882d32f | 225efb9c-4bfa-42fc-a67d-a5f76c9c86a4 | MPP-77 | Roadside Kit | New Product Development | 2025-08-01 | 2025-09-30 |  |  | OPEX |  |  | Regular | 42 | 2025-07-14T20:55:10Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2025 Q3 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | f755ef1e-9bac-46a9-a6d3-bcb5fa195a64 | 7ad26876-bac9-4686-b07c-29239c4e76e3 | MPP-78 | Mossy Oak | New Product Development | 2025-08-01 | 2025-09-30 |  |  | OPEX |  |  | Regular | 43 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2025 Q3 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | c47738d1-794f-43e2-848d-4b717b95afff | 26ff3fd7-c910-4974-bc52-6ed069b9ec94 | MPP-79 | 2026 Q1 Kit | New Product Development | 2026-01-01 | 2026-03-31 |  |  | OPEX |  |  | Regular | 44 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2026 Q1 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 70ea3f87-1efc-4886-bbda-83ac0669a27b | 6ed322ad-7daf-4d91-8fc8-ba393107fcb7 | MPP-80 | 2026 Q1 Colors | New Product Development | 2026-01-01 | 2026-03-31 |  |  | OPEX |  |  | Regular | 45 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2026 Q1 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 02b2b4f0-0c85-4eda-aede-bfdcf85a4898 | 5dcb863f-040c-40b6-b283-4a44905b31bf | MPP-81 | 2026 Q3 Kit | New Product Development | 2026-07-01 | 2026-09-30 |  |  | OPEX |  |  | Regular | 46 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2026 Q3 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | d6df04d9-0748-4092-84d6-2cdf414d3106 | 0b549695-ddac-4962-9e45-b66bca9306ec | MPP-82 | 2026 Q3 Colors | New Product Development | 2026-07-01 | 2026-09-30 |  |  | OPEX |  |  | Regular | 47 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2026 Q3 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 10eee9f6-ab58-4415-ab74-dae6227e5797 | 6d7f9c41-dc50-4058-ba4e-465cc2234097 | MPP-83 | 2027 Q1 Kit | New Product Development | 2027-01-01 | 2027-03-31 |  |  | OPEX |  |  | Regular | 48 | 2025-07-10T21:13:54Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | On-going | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 78497372-e7b2-4045-a543-d4f5f839efea | d721745c-bd7e-4020-9fc4-0c4737368147 | MPP-84 | 2027 Q1 Colors | New Product Development | 2027-01-01 | 2027-03-31 |  |  | OPEX |  |  | Regular | 49 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2027 Q1 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 7b2cfa6a-2bf8-4561-a8d3-eb7962685228 | 33f64b97-5861-4813-a2f4-7ccc985370d7 | MPP-86 | 2027 Q3 Colors | New Product Development | 2027-07-01 | 2027-09-30 |  |  | OPEX |  |  | Regular | 50 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2027 Q3 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 47b250d3-ebc5-4b45-93f7-f48ceb17ef1a | 8b756ed3-c095-408d-9403-da6840a3d6a0 | MPP-85 | 2027 Q3 Kit | New Product Development | 2027-07-01 | 2027-09-30 |  |  | OPEX |  |  | Regular | 51 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2027 Q3 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 30aa9cba-2386-42aa-87d6-e4424e5acd32 | 02baeb79-50e6-4b38-b9a2-9045736dee44 | MPP-70 | Soft Tonneau Cover | New Product Development | 2025-11-01 | 2028-06-30 |  |  | OPEX |  |  | Regular | 52 | 2025-07-10T16:24:57Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2028 Q1 | No | VEHICLE EXPANSION |  |  | Flagship |  |  |  |  | 5. Other Vehicle
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 96d0ed3c-eae3-491b-b0cb-6829d1c3e007 | 8765c748-3cd7-4d64-bd55-8a4825cfb989 | MPP-87 | 2028 Q1 Kit | New Product Development | 2028-01-01 | 2028-03-31 |  |  | OPEX |  |  | Regular | 53 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2028 Q1 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | c9563b7a-ca9d-42f9-8775-649f23c635e1 | 4a84a941-4d0b-4ee9-a892-730c0447f4ae | MPP-88 | 2028 Q1 Colors | New Product Development | 2028-01-01 | 2028-03-31 |  |  | OPEX |  |  | Regular | 54 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2028 Q1 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 849c6f3c-d59e-433b-8e60-4a70c937432e | 15b575ce-108e-42fa-94c0-32d592c8e73e | MPP-89 | 2028 Q3 Kit | New Product Development | 2028-07-01 | 2028-09-30 |  |  | OPEX |  |  | Regular | 55 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2028 Q3 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > b. Kits
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 4dc9c1f8-b2f3-4062-8b23-244481379a9d | e8795f99-3a5f-4e4f-ab93-5907ed60b5fb | MPP-90 | 2028 Q3 Colors | New Product Development | 2028-07-01 | 2028-09-30 |  |  | OPEX |  |  | Regular | 56 | 2025-07-10T19:34:28Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2028 Q3 | No | EXPAND D-CO |  |  | Small |  |  |  |  | 6. D-cosystem > d. Colorways
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 7d9e14cc-aa91-44e4-baab-601fd566d044 | eb88bf25-1d6c-42a8-9a18-d1701907d4ce | MPP-91 | Manufacturing Initiatives | Continuous Improvement | 2025-01-01 | 2030-12-31 |  |  | OPEX |  |  | Regular | 57 | 2025-07-14T17:51:51Z | 2628.8 | 2628.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2628.8 | 2628.8 | 2628.8 | 0 | 0 | 0 |  |  |  | 0 | On-going | No | CI
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 74f73a8c-5258-47d9-9395-8ab48ca505ce | be033a8d-a54f-4d53-8c1e-a8d1e4e25d3f | MPP-92 | Biz Dev / Strategy | Business Development | 2025-01-01 | 2030-12-31 |  |  | OPEX |  |  | Regular | 58 | 2025-07-14T17:51:51Z | 1238.4 | 1238.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209.6 | 1209.6 | 1238.4 | 0 | 0 | 0 |  |  |  | 0.023256 | On-going | No | CI
7a36777f-00d7-dd0b-2468-95aa94f90e63 | Plan of Record | 4ffb996d-e2d8-42d7-b787-b75015b0f1f5 | ca977903-13a5-43b0-a832-66487a04bd50 | MPP-93 | Dept Internal | Continuous Improvement | 2025-01-01 | 2030-12-31 |  |  | OPEX |  |  | Regular | 59 | 2025-07-14T17:51:51Z | 1390.4 | 1390.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354.4 | 1354.4 | 1390.4 | 0 | 0 | 0 |  |  |  | 0.025892 | On-going | No | CI